## Instructions
INDUSTRY ACADEMIA COMMUNITY
DOMAIN NAME:
INTERN NAME:
PROJECT NAME:
DOCUMENT NAME: | Lessons Learnt Log
CREATED ON: | DD-MMM-YYYY
Purpose of Document
Lessons Learned Logs are used to capture and share knowledge about what has worked well and what could have been done differently during the planning, management and delivery of an improvement project.
They help others learn from the project team's experience. Lesson Learned Logs: Help support a learning culture.
INSTRUCTIONS:
1. Text in Italics are instructions for completing the document
2. Text in orange is just for reference and should be deleted before submitting the document
3. Comments may be added to some of the cells, please read the comments to better understand the terms
4. All fields must be duly filled
5. The descriptions for what to be filled in each of the fields are provided in the template.
6. Clear all the sample data/instructions provided in the template. The data/instruction provided is only for reference purposes.

## LESSONS LEARNED
LESSONS LEARNED
DOCUMENT VERSION: 1.0
PROJECT NAME | Predictive Models for Student Placement and Graduation Year |  |  |  | PLEASE GO THROUGH THE INSTRUCTION SHEET PROVIDED TO GET AN UNDERSTANDING OF HOW TO USE THIS TEMPLATE.
PROJECT ID
PROJECT MANAGER | Harshada Topale
PROJECT SPONSOR | Cloud Counselage Pvt Ltd.
SL. NO | DATE RAISED | EVENT | LESSON CATEGORY | EARLY WARNING SIGNS? | RECOMMENDATIONS | ACTIONS | OWNER | STATUS | ADDITIONAL COMMENTS
| MENTION THE DATE ON WHICH THE MATTER WAS RAISED | DESCRIBE THE EVENT THAT WAS RAISED | MENTION WHICH CATEGORY THE EVENT WAS RELATED TO | MENTION YES OR NO | MENTION THE RECOMMENDATIONS THAT WAS SUGGESTED FOR SOLVING THE EVENT IF ANY | MENTION THE ACTION SELECTED FOR SOLVING THE VENT | MENTION THE RESPONSIBLE PERSON FOR SOLVING THE EVENT | SOLVED/ PENDING | MENTION IF ANYTHING ELSE OCCURRED DURING THE TIME OF THE MENTIONED EVENT
1 | 2025-01-04 | Encountered errors while handling non-numeric data types | Issue | No | Ensure to preprocess and clean data before model fitting | Preprocess and encode non-numeric data types | Project Engineer | Solved | Improved data preprocessing steps
2 | 2025-01-04 | RandomForestClassifier not handling NaN values | Issue | No | Use appropriate imputation techniques for missing values | Implemented SimpleImputer for NaNs | Project Engineer | Solved | None
3 | 2025-01-05 | TypeError due to mixed data types in a single column | Issue | No | Ensure uniform data types in each column | Converted mixed type columns to strings | Project Engineer | Solved | None
4 | 2025-01-06 | Missing FunctionTransformer import causing errors | Issue | No | Double-check imports and ensure all dependencies are included | Added missing imports | Project Engineer | Solved | Added import for FunctionTransformer
5 | 2025-01-07 | ValueError due to NaN values during model training | Risk | No | Implement robust data validation and cleaning steps | Verified and cleaned all data inputs | Project Engineer | Solved | Ensured all steps handle NaN values
6 | 2025-01-07 | Difficulty in transforming categorical data | Issue | No | Use Pipelines for systematic preprocessing | Applied ColumnTransformer and Pipeline | Project Engineer | Solved | Simplified data transformation process
7 | 2025-01-07 | Errors during prediction on test data | Issue | No | Validate and preprocess test data similarly to training data | Applied same preprocessing steps to test data | Project Engineer | Solved | Consistent preprocessing for test data
8 | 2025-01-07 | Difficulty in feature importance interpretation | Issue | No | Use SHAP or LIME for better interpretability of model | Applied SHAP to interpret feature importance | Project Engineer | Solved | Improved understanding of model behavior
9 | 2025-01-08 | Incomplete data columns causing issues during imputation | Issue | No | Ensure all columns have complete data before imputation | Performed data integrity checks | Project Engineer | Solved | Added checks for data completeness
10 | 2025-01-08 | High dimensionality in one-hot encoded data causing slow training | Risk | Yes | Consider dimensionality reduction techniques | Used PCA for dimensionality reduction | Project Engineer | Solved | Improved model training speed
11 | 2025-01-08 | Long training times due to large dataset | Risk | Yes | Optimize model parameters and use a more efficient algorithm | Conducted hyperparameter tuning and used LightGBM | Project Engineer | Solved | Reduced training time significantly
12 | 2025-01-08 | Inconsistent results across different runs | Issue | Yes | Ensure reproducibility by setting random seeds | Set random_state in all model and preprocessing steps | Project Engineer | Solved | Consistent results achieved
13 | 2025-01-09 | Issues with imbalanced target classes | Risk | Yes | Apply resampling techniques to balance classes | Implemented SMOTE for oversampling | Project Engineer | Solved | Improved model performance on minority class
14 | 2025-01-09 | Overfitting detected during cross-validation | Risk | Yes | Use regularization techniques and cross-validation | Implemented regularization and performed cross-validation | Project Engineer | Solved | Reduced overfitting, better generalization
15 | 2025-01-10 | Difficulty in tracking changes and debugging issues | Dependence | Yes | Maintain a detailed development log | Created and updated development log | Project Engineer | Solved | Facilitated better tracking and debugging
16 | 2025-01-10 | Errors in final output file formatting | Issue | No | Verify and format output file as per requirements | Applied data formatting checks and corrections | Project Engineer | Solved | Correctly formatted output file
17 | 2025-01-10 | Difficulty in integrating different parts of the code | Dependence | Yes | Modularize code and use version control effectively | Refactored code into modules and used Git | Project Engineer | Solved | Easier integration and collaboration
18 | 2025-01-10 | Problems with deploying the model | Issue | Yes | Use containerization for deployment | Deployed model using Docker containers | Project Engineer | Solved | Smooth deployment process
19 | 2025-01-10 | Stakeholder communication gaps | Issue | Yes | Regular updates and clear communication channels | Set up regular meetings and communication protocols | Project Engineer | Solved | Improved stakeholder satisfaction
20 | 2025-01-11 | Lack of documentation leading to confusion | Issue | Yes | Maintain comprehensive documentation of the project | Created detailed project documentation | Project Engineer | Solved | Clearer understanding for all team members